## Sheet 1
Maximum Reserve Capacity Price Working Group: Work Programme Calendar (draft)
|  | Resource(s) | Related procedure? |  | 2010-06-01 |  |  |  | 2010-07-01 |  |  |  |  | 2010-08-01 |  |  |  | 2010-09-01 |  |  |  | 2010-10-01
|  |  |  | 28/5 | 4/6 | 11/6 | 18/6 | 25/6 | 2/7 | 9/7 | 16/7 | 23/7 | 30/7 | 6/8 | 13/8 | 20/8 | 27/8 | 3/9 | 10/9 | 17/9 | 24/9 | 1/10 | 8/10 | 15/10 | 22/10 | 29/10
| MAC meeting dates | [5 empty] | 16th |  |  |  |  | 19/20 |  |  | 11th |  |  |  | 8th |  |  |  |  | 13th
| MRCPWG meeting dates |  |  |  | 31st |  |  | 22nd | 2nd | [6 empty] | 17th |  | 30th |  | 15th |  | 29th
Meeting 1
| Meeting Papers circulated to members |  |  | √
| MRCPWG Meeting 1 (31 May 2010) |  |  |  | √
| Finalise Scope of Work |  |  |  | √
| Finalise Work Programme |  |  |  | √
| Papers circulated to MAC |  |  |  |  | √
| MAC Meeting (membership noted and work programme approved) | [5 empty] | √
Meeting 2
| Meeting Papers circulated to members | [5 empty] | √
| MRCPWG Meeting 2 (22 June 2010) | [6 empty] | √
| Determine Consultancy Scope of Work (if required) | [6 empty] | √
| Draft Tender documents (IMO) | [6 empty] | √
Meeting 3
| Meeting Papers circulated to members | [6 empty] | √
| MRCPWG Meeting 3 (2 July 2010) | [7 empty] | √
| Finalise Tender documents | [7 empty] | √
| Update Papers circulated to MAC | [9 empty] | √
| MAC Meeting | [10 empty] | √
Meeting 4
| Meeting Papers circulated to members | [13 empty] | √
| MRCPWG Meeting 4 (17 August 2010) | [14 empty] | √
| Presentation of initial prelminary results | [14 empty] | √
Meeting 5
| Meeting Papers circulated to members | [15 empty] | √
| MRCPWG Meeting 5 (30 August 2010) | [16 empty] | √
| Draft Results Presented | [16 empty] | √
| Papers circulated to MAC | [16 empty] | √
| MAC Meeting | [17 empty] | √
Meeting 6 & 7
| Meeting Papers circulated to members | [17 empty] | √ |  | √
| MRCPWG Meeting 6 (15 September 2010) | [18 empty] | √
| MRCPWG Meeting 7 (29 September 2010) | [20 empty] | √
Final Results
Detailed procedure change development
Draft initial amended Market Procedure and Procedure Change Proposal
Working Group discuss detailed amended Market Procedure and Procedure Change Proposal
Finalise amended Market Procedure and Procedure Change Proposal
Papers circulated to MAC
MAC meeting (Pre procedure change discussion paper)
Procedure Change Process
Formal submission of proposed amended Market Procedure
Consultation Period
Procedure Change Final Report
Board approval of final report
Implementation
Key
| MRCPWG Meeting Date |  |  | √
Dates to be determined