## Milestone Log
Foundation Regulatory Frameworks - Joint Industry Plan - Milestone Log
ID | Title | Project/Topic | Type | Milestone Date | Date Status | Owner | Level | Description | Dependencies | Status/Comments
JM-051 | Limit Advice Development - Initial Set of Thermal Limits provided to AEMO | Constraints | Business Process | 2020-04-30 | Complete | Western Power | 1 | Thermal limit advice to AEMO initial set (non RCM limit advice)
JM-068 | Limit Advice Development - N-0 System Normal Limit Advice to AEMO | Constraints | Business Process | 2020-08-31 | Complete | Western Power | 2 | System Normal (N-0) non-thermal limit advice to AEMO | JM-051
JM-066 | Constrained Access Process Applies to New Access Offers | Connections | Business Process | 2020-09-18 | Complete | Western Power | 1 | The Electricity Networks Access Code Amendments (No. 2) 2020 were gazetted 18 September - no further firm (unconstrained) services for generator connections
JM-004 | Limit Advice Requirements Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-005 | Constraint Formulation Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-007 | Real Time Market – Dispatch Instructions & Conversions Procedure Consultation Start | WEMDE/Dispatch | WEM Procedure Milestone | 2020-10-29 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic
JM-006 | Constraint Information Resource Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-11-05 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-012 | GPS Testing Requirements Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic
JM-013 | GPS Monitoring Plan & Template Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-014 | GPS Process & Transition Considerations Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-018 | Credible Contingency Events Procedure Consultation Start | System Planning (e.g. Outages, PASA) | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-047 | GPS Submission Template provided to Market Participants | GPS | Business Process | 2020-12-01 | Complete | Western Power | 1 | Provide GPS information capture template to Market Participants
JM-039 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation
JM-044 | WEM Procedure - Generation System Model Submission and Maintenance - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation
JM-040 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation | JM-039
JM-045 | WEM Procedure - Generation System Model Submission and Maintenance - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation | JM-045
JM-015 | GPS Testing Requirements Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-016 | GPS Monitoring Plan & Template Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-017 | GPS Process & Transition Considerations Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-019 | Credible Contingency Events Procedure Consultation Live | System Planning (e.g. Outages, PASA) | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-082 | Settlements Enhancements technical specifications available | Settlements | Technical Information Release | 2021-02-01 | Confirmed | AEMO | 1
JM-048 | Draft GPS Submissions Received from Market Participants | GPS | Business Process | 2021-03-31 | Complete | Western Power | 1 | Receive draft GPS information capture template back from Market Participants. Action undertaken by Market Participants. Consult with Western Power as required. | JM-047
JM-030 | Minister Approves Tranche 4a Rule Changes | Regulatory | Significant Market Milestone | 2021-04-30 | Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 4: Transitional Arrangements (e.g. ESS accreditation) Tranche 5: Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework
JM-028 | GPS Market Trial | GPS | Technical Information Release | 2021-06-28 | Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  | Market Trial is still ongoing as at 27/08/2021; Check again at 30/09/21
JM-094 | Pinjar comms link complete | Site Works (Synergy) | Technical Implementation | 2021-06-30 | Complete | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069
JM-022 | Settlements (Reform) Interface Details Available | Settlements | Technical Information Release | 2021-07-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-078 | Completion of operator recruitment Ph 1 | Operational Capabilities (Synergy) | Training | 2021-07-01 | Complete | Synergy | 1
JM-083 | Settlement Enhancements Market Trial | Settlements | Technical Implementation | 2021-07-01 | Confirmed | AEMO | 1
JM-029 | AEMO GPS Repository Live | GPS | Technical Go-Live | 2021-07-28 | Complete | AEMO | 1 | GPS Repository completes formal testing and moves to Production environment.
JM-031 | Connection Application Form Updated for Constrained Access | Connections | Business Process | 2021-07-31 | Complete | Western Power | 1 | Updated customer connection application form (including information for generator performance standards) Dependant on the approval of Access Code Tranche 2 amendments. | JM-032
JM-032 | Revised Applications and Queuing Policy (AQP) and Contribution Policy Published | Regulatory | Business Process | 2021-07-31 | To Be Confirmed | Western Power |  | Revised Applications and Queuing Policy, ETAC and Contributions Policy for constrained access (ETIU to consult industry and gazettal) Dependant on the approval of Access Code Tranche 2 amendments.
JM-085 | Tranche 1 Procedures Complete (RCM) | Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone | 2021-08-01 | Complete | AEMO | 1 |  |  | Date slip from July to August 2021, but now complete.
JM-084 | Settlement Enhancements Go Live | Settlements | Technical Go-Live | 2021-08-01 | Confirmed | AEMO | 1
JM-070 | Control room complete | Site Works (Synergy) | Technical Implementation | 2021-09-01 | Confirmed | Synergy | 1
JM-079 | Completion of trader recruitment Ph1 | Operational Capabilities (Synergy) | Training | 2021-09-01 | Complete | Synergy | 1
JM-090 | Settlements Enhancments Release 2 Go Live | Settlements | Technical Go-Live | 2021-09-01 | Confirmed | AEMO | 1
JM-021 | RTMS technical specifications available | WEMDE/Dispatch | Technical Information Release | 2021-09-17 | Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  | AEMO plans to release a draft version 0.4 to the market in September 2021 to support training prior to MARKET TEST.
JM-055 | RCM 2021 Cycle - AEMO provides EOI and Facility Closure Info | Reserve Capacity Mechanism (RCM) | Business Process | 2021-09-30 | Confirmed | AEMO | 1 | AEMO provides WP EOI and Facility Closure Info
JM-071 | Pinjar Control Network works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-074 | Western Power SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-095 | Kemerton comms link complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069
JM-096 | Completion of operator recruitment Ph 2 | Operational Capabilities (Synergy) | Training | 2021-10-01 | Confirmed | Synergy | 1 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting
JM-086 | Phase 1 Market Trial Commences (RCM) | Reserve Capacity Mechanism (RCM) | Technical Implementation | 2021-10-15 | Confirmed | AEMO | 1
JM-072 | Site SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-073 | Control systems works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-075 | Application development complete – core trading system | Technology (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-093 | RTMS Market Test Commence | WEMDE/Dispatch | Staging Deployment | 2021-11-10 | Confirmed | AEMO | 1
JM-020 | WEMDE technical specifications available | WEMDE/Dispatch | Technical Information Release | 2021-12-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-080 | Commencement of GT transition planning | Operational Capabilities (Synergy) | Business Process | 2021-12-01 | Confirmed | Synergy | 1
JM-087 | Phase 1 Go Live (RCM) | Reserve Capacity Mechanism (RCM) | Technical Go-Live | 2021-12-01 | Confirmed | AEMO | 1
JM-089 | Minister Approves Tranche 5 Rule Changes | Regulatory | Significant Market Milestone | 2021-12-01 | Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework
JM-052 | Limit Advice Development - N-1 and N-1-1 Priority 1 Limit Advice to AEMO | Constraints | Business Process | 2022-01-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 1 | JM-068
JM-023 | Outage Management technical specifications available | System Planning (e.g. Outages, PASA) | Technical Information Release | 2022-02-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-049 | GPS Updates provided to AEMO GPS Repository | GPS | Business Process | 2022-02-28 | Confirmed | Western Power |  | GPS transition finalised with Market Participants and documented in Generator Register | JM-029
JM-091 | RCM (Year 1 of 2021 RC Cycle) technical specifications available | Reserve Capacity Mechanism (RCM) | Technical Information Release | 2022-02-28 | Confirmed | AEMO | 1 | RCM Phase 1 of 2021 RC Cycle, release 3 (R1.2 API Spec version) will complete this first phase of RCM work
JM-056 | RCM 2021 Cycle – RCM Limit Advice provided to AEMO | Reserve Capacity Mechanism (RCM) | Business Process | 2022-03-01 | To Be Confirmed | Western Power |  | WP provides AEMO RCM Limit Advice based on AEMO's provision of RCM Requirements
JM-081 | Completion of trader recruitment Ph2 | Operational Capabilities (Synergy) | Training | 2022-03-01 | Confirmed | Synergy | 1
JM-024 | Commissioning Test technical specifications available | System Planning (e.g. Outages, PASA) | Technical Information Release | 2022-04-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-058 | Weekly Settlement - WP and AEMO Interface - Ready for Trials | Settlements | Technical Implementation | 2022-04-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B Settlement interface ready for trials | JM-057
JM-063 | Outage Management WP and AEMO Interface - Ready for Trials | System Planning (e.g. Outages, PASA) | Technical Implementation | 2022-04-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for trials | JM-062
JM-002 | Market Trial Commences | Program/Implementation | Significant Market Milestone | 2022-04-01 | To Be Confirmed | AEMO | 0 | Commencement of 'formal' Market Trial period where Market Participants and other parties will conduct defined end-to-end scenario based trials e.g. as opposed to purely system/user integration testing). |  | Scope of Market Trial and Dates to be developed via WRIG
JM-077 | Migration planning and execution | Technology (Synergy) | Technical Implementation | 2022-05-01 | Confirmed | Synergy | 1
JM-043 | Loss Factors Provided for New Market |  | Business Process | 2022-06-01 | Confirmed | Western Power |  | Finalise procedure post industry consultation | JM-042
JM-076 | Development complete – reconciliation and settlement | Technology (Synergy) | Technical Implementation | 2022-08-01 | Confirmed | Synergy | 1
JM-053 | Limit Advice Development - N-1 and N-1-1 Priority 2 Limit Advice to AEMO | Constraints | Business Process | 2022-10-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 2 | JM-052
JM-064 | Outage Management WP and AEMO Interface - Ready for Market Start | System Planning (e.g. Outages, PASA) | Technical Implementation | 2022-10-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for market start | JM-063
JM-003 | SCED Go Live | Program/Implementation | Significant Market Milestone | 2022-10-01 | Confirmed | AEMO | 0 | Date on which first interval of Security Constrained Economic Dispatch (SCED) will take place in line with commencement of relevant WEM Rule Modifications and Go Live date referenced in WEM Rule 1.20. |  | Specific scope of Go Live milestone to be refined and defined via WRIG
JM-008 | Constraint Information Resource Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-009 | Limit Advice Requirements Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-010 | Constraint Equation Development Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-011 | Real Time Market – Dispatch Instructions & Conversions Live | WEMDE/Dispatch | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-033 | Generator Interim Access (GIA) service ceases and dispatched using SCED | WEMDE/Dispatch | Technical Go-Live | 2022-10-01 | To Be Confirmed | AEMO |  | GIA operation ceases and transition each facility to SCED control - assumed at Market Start 1 Oct 2022 |  | Likley to be merged with the SCED Go Live milestone as one component of that activity.
JM-054 | Limit Advice Development - N-1 and N-1-1 Priority 3 Limit Advice to AEMO | Constraints | Business Process | 2023-06-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 3 | JM-053
JM-088 | Minister Approves Tranche 4b Rule Changes | Regulatory | Significant Market Milestone | Jul/Aug-21 | Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework
JM-001 | Minister Approves Tranche 1-3 Rule Changes | Regulatory | Significant Market Milestone | Nov-Dec-20 | Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 1 (Nov-20): Generator Performance Standards Framework (incl. Ch. 3a, Appendix 12, and transitional rules) ‘Administrative Package’ Frequency Operating Standards and Contingency Events Frameworks Tranche 2 (Dec-20): Foundation Market Parameters (incl. STEM) Frequency Co-optimised ESS Operating States and Tech Envelope Scheduling and Dispatch Outage Management and Commissioning Tests Operational Planning (PASA) WEM Monitoring and Compliance Market Settlement Tranche 3 (Dec-20): Reserve Capacity Mechanism (RCM) Prioritisation and Network Access Quantities Framework Participation of storage and hybrid facilities in the RCM RCM changes consequential to SCED Application and Queuing Policy for Constrained Network Access |  | On Track - all three Tranches published for consultation in October 20
JM-034 | Terminate GIA Related NCS | Connections | Business Process | Post 1-Oct 22 | Confirmed | Western Power | 1 | Termination of GIA related Network Control Service after new market start in conjunction with any required contract amendments for constrained access
JM-038 | WEM Procedure - Limit Advice Development - Procedure Live | Constraints | WEM Procedure Milestone | Q1 2022 | To Be Confirmed | Western Power | 1 | Finalise procedure post consultation | JM-037
JM-037 | WEM Procedure - Limit Advice Development - Consultation Start | Constraints | WEM Procedure Milestone | Q1-2022 | To Be Confirmed | Western Power | 1 | Procedure updated to include RCM limit advice requirements
JM-042 | WEM Procedure - Loss Factors - Procedure Live |  | WEM Procedure Milestone | Q2-2022 | To Be Confirmed | Western Power |  | Draft procedure consultation closed | JM-041
JM-041 | WEM Procedure - Loss Factors - Consultation Start |  | WEM Procedure Milestone | Q2-2022 | To Be Confirmed | Western Power |  | Draft procedure complete and commence 4 weeks industry consultation
JM-027 | Registration technical specifications available | Registrations | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-025 | PASA technical specifications available | System Planning (e.g. Outages, PASA) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-092 | RCM (Year 3 of 2021 RC Cycle) technical specifications available | Reserve Capacity Mechanism (RCM) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1
JM-026 | STEM technical specifications available | STEM | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-057 | Weekly Settlement - WP and AEMO Interface - Ready for Test | Settlements | Technical Implementation |  | To Be Confirmed | Western Power |  | WP and AEMO B2B Settlement interface ready for test | JM-022
JM-062 | Outage Management WP and AEMO Interface - Ready for Test | System Planning (e.g. Outages, PASA) | Technical Implementation |  | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for test | JM-023
JM-036 | Western Power SCADA Works Complete (Non-Synergy) | WEMDE/Dispatch | Technical Implementation |  | To Be Confirmed | Western Power |  | Completion of SCADA upgrades / changes to meet AEMO SCED requirements (Note - required timeframe for market trials to be confirmed by AEMO/ WRIG) | JM-035
JM-059 | Outage Intention Plan - Outage Intention Plan Specification Available | System Planning (e.g. Outages, PASA) | Technical Information Release |  | To Be Confirmed | AEMO |  | Develop system to transfer Outage Intention Plan to AEMO - Test | JM-058
JM-035 | Market Participant SCADA Requirements Provided to Western Power | WEMDE/Dispatch | Technical Implementation |  | To Be Confirmed | Western Power |  | Market Participants identify requirements for SCADA upgrades / changes to meet AEMO SCED requirements and provide to Western Power.
JM-097
JM-098
JM-099
JM-100
JM-101
JM-102
JM-103
JM-104
JM-105
JM-106
JM-107
JM-108
JM-109
JM-110
JM-111
JM-112
JM-113
JM-114
JM-115
JM-116
JM-117
JM-118
JM-119
JM-120
JM-121
JM-122
JM-123
JM-124
JM-125
JM-126
JM-127
JM-128
JM-129
JM-130
JM-131
JM-132
JM-133
JM-134
Potential Milestones - TBC
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 0 - Significant 'Program Milestone' relevant to majority/all stakeholders and Market Particpants Level 1 - Significant 'Implementation Milestone' relevant to majority of stakeholders Level 2 - Important 'Implementation Milestone' relevant to one or small number of stakeholders or Market Particpants OR a preliminary milestone (e.g. early consultation in advance of formal consultation on a WEM Procedure)
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be updated, but cannot be updated yet.
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 31/08/21 [Confirmed to complete] - see email from Mark McKinnon to Mike Reid same day
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 31/08/21 [removed some minor details] - see email from Mark McKinnon to Mike Reid same day
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 26/08/21, Mike changed date from July to August
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mike replaced 1/05/21 based on WRIG-IT dates from 26/08 presentation
Note on G41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contingent of Erika and team keeping to the 31 August commitment from WRIG-IT 26/08
Note on C42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed initials WP as believe MP was intended.
Note on F42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Edited based on discussion with Nicki 27.08.21
Note on F51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mike replaced 1/09/2021 with 10/11/2021 based on WRIG-IT presentation of 26/08/2021
Note on C52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on B57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dino to check if current
Note on C59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on F59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from August 2021
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dino to check if current
Note on C62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on C85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on C86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"
Note on C87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This (Y3) milestone should identify that it relates to the 2021 RC Cycle. This milestone described by Bec Petchey's WRIG-IT presentation in August as: "Changes to Reserve Capacity Testing and Reserve Capacity Obligation Quantities to reflect the introduction of components in the 2021 Reserve Capacity Cycle"
Note on C88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replaced "Interface Details Available" with "technical specifications available"

## (Major) Change Log
JIP Release Date | Change Description
2020-12-17 | Initial set of Western Power and Synery Milestones added
2021-07-22 | Synergy milestones added (JM-094,JM-095, JM-096); Western Power milestones deleted (JM-046, JM-050, JM-060, JM-061, JM-065, JM-067) and various edits to WP titles, timings and dependencies; JM-028, 029, 083, 084 - minor date changes; JM-085 Status change confirmed to complete
2021-09-02 | Synergy milestone JM-069 deleted since this was replaced with JM-094 and JM-095
2021-09-02 | AEMO changes JM-085: Changed from 1/07 to 1/08/2021; JM-021: Changed from 1/05 to 17/09/2021; JM-055: Added a date (30/09/2021), where previously there was no date. Removed “WP” [believe was intended to be MPs]; JM-093: Replaced 1/09/2021 with 10/11/2021 based on WRIG-IT presentation of 26/08; JM-091: Modified name to clarify. Changed date from August 2021 to 28/02/2022; JM-023: Changed from 1/09/2021 to 1/02/2022; JM-024: Changed from 1/11/2021 to 1/04/2022; Also replaced "Interface Details Available" with "technical specifications available" for all AEMO milestones using the phrase

## Issue Log
ID | Issue | Raised by | Date | Status/Updates

## Lookups
Project/Topic | Type | Date Status | Owner
Connections | Business Process | To Be Confirmed | AEMO
Constraints | Significant Market Milestone | Confirmed | ERA
Generator Interim Acces (GIA) | Staging Deployment | Complete | ETIU
GPS | Technical Go-Live |  | IPPs
Program/Implementation | Technical Implementation |  | Retailers
Registrations | Technical Information Release |  | Synergy
Regulatory | Training |  | Western Power
Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone
Settlements
STEM
System Planning (e.g. Outages, PASA)
WEMDE/Dispatch
Site Works (Synergy)
Technology (Synergy)
Operational Capabilities (Synergy)
Contract Remeidation (Synergy)