## Introduction
Contract Management Workbook - Single Contractor
Introduction
To maximise the achievement of contractual outcomes and to continually improve contract performance, effective contract management is required. This workbook has been designed to support contract managers by providing a tool to record key contract information in a single place. This workbook: - is designed to be a working document which is updated frequently; - should be used in the management contracts with a single supplier; and - should not be used for simple contracts or those with a panel of suppliers. There are other workbooks that can be used to support the management of those types of contracts, available on WA.gov.au. Agencies may modify the Workbooks to suit individual requirements. Agencies acknowledge that they will retain ownership and responsibility for its maintenance, and the input and management of all content including modifications. Agencies may use Agency specific workbooks as an alternative option. Each tab has a brief set of instructions in red text.
More Information
More information to support your contract management activities can be found on the Department of Finance's pages on wa.gov.au. Please use the links below to access the support resources.
Contract Management templates
Contract Management guidelines
Contract Management training - online
Contract Management training - face to face

## Key Contract Details
Key Contract Details
Contract Overview
Agency Name: |  | Work Area:
Contract Manager: |  | Contract No. & Title:
Contract Term: |  | Initial Term: |  | Extension options:
Contract Commencement Date: |  | Contract Expiry Date: (inc of all extension options) |  | Total Contract Value: (full contract term inc of GST)
Contract Objectives and Scope:
Extension Options
Extension | Due Date | Exercised | Date Exercised or Declined | Comments | File/RMS Reference No.
Option 1 |  | Yes / No
Option 2 |  | Yes / No
Option 3 |  | Yes / No
Option 4 |  | Yes / No
Contractor Details
Contractor Name: |  | Contact person:
Address: |  | Position:
ABN: |  | Telephone:
ACN: |  | Email:
Contract Variations and Adjustments
Note: - Adjustments are changes that are permitted by the contract (for example annual price increases due to CPI fluctuations). - If a variation changes the price, contract term etc the Purchase Order may need to be updated. - If a variation changes the total contract value, you may need to record this variation on Tenders WA.
Variation/Adjustment No. | Description / Reason | Date Effective From | Current Total Contract Value inc GST | New Total Contract Value inc GST | Entered on Tenders WA | File / RMS Reference
Yes / No
Yes / No
add rows as needed |  |  |  |  | Yes / No
Insurance Details
Insurance Type | Expiry Date | Status | Insurer | Policy No. | Insured Amount | File / RMS Reference No.
e.g. Public Liability
e.g. Professional Indemnity
e.g. Workers Compensation
add rows as needed
Formulas:
Initial Term: = IF(([Due Date])=0," ",IF([Due Date]<TODAY(),"Expired",IF([Due Date]<(TODAY()+#REF!),"Expiring","Current")))

## Document Register
Document Register
Use the table below to record the file references of the key documents related to the procurement process and management of the contract
Contract Documents | File / RMS Reference No.
Request Conditions and General Conditions of Contract - [INSERT VERSION - e.g. October 2020] (must be the same version as listed in the Request)
Request
Addenda (if any)
Contractor's Offer including any clarifications
Letter of Award (signed copy)
Service Level Agreement (if applicable) (signed copy)
Other Documents
Business Case (where completed) (approved copy)
Evaluation Report (approved and signed copy)
Preferred Respondent Letter(s) (signed copy)
Preferred Respondent Response(s) / Outcome(s)
Unsuccessful Letter(s) (signed copy)
Add relevant documents as created

## Pricing and Payments
Pricing and Payments
Pricing details
Price Schedule | Insert details from the Contractor's response to the Request
Price Variation Mechanism | Insert details from the Request
Settlement Discount details (if applicable) | e.g. ….% discount where payment of the Price or that part of the Price specified in the invoice is made within (x) Calendar Days of the date of the invoice
Payment Schedule details (if applicable)
Payments made
Contract Value inc GST
Balance Remaining
| Date Processed | Payment Amount | Comments
Payments Made
Total Payments Made

## Performance Measurement
Performance Measurement
Use the table below to detail the contract KPIs and the Contractor's performance against them. Add rows as needed.
Specified Output / Service | Agreed Performance Measures | Proposed Method of Measurement | Measurement Date | Result / Analysis Comments | File/RMS Reference No.

## Risk Register
Risk Register
Use the table below to record the contract risks and any mitigation strategies in place. More information on how to use the table can be found in the Risk Workbook available on WA.gov.au. Add rows as needed.
Activity / Event / Process / Product / Service | Risk Ref No.^ | Risk | Causes | Controls | Consequences | Risk level | Action(s) | Residual Risk
|  | What can go wrong? | What could potentially cause that to happen? | Mechanisms in place to prevent or mitigate the event occurring or limit its impact. | What are the potential results? | Refer to State Agency’s risk ref tables & take existing controls into account. | What action(s) if any will you take to treat the risk? Who is responsible and when should this occur? | Predicted level of risk after action/s.
[6 empty] | Likelihood: |  | Likelihood:
[6 empty] | Consequence: |  | Consequence:
[6 empty] | Level of Risk: |  | Level of Risk:
[6 empty] | Likelihood: |  | Likelihood:
[6 empty] | Consequence: |  | Consequence:
[6 empty] | Level of Risk: |  | Level of Risk:
[6 empty] | Likelihood: |  | Likelihood:
[6 empty] | Consequence: |  | Consequence:
[6 empty] | Level of Risk: |  | Level of Risk:
[6 empty] | Likelihood: |  | Likelihood:
[6 empty] | Consequence: |  | Consequence:
[6 empty] | Level of Risk: |  | Level of Risk:
[6 empty] | Likelihood: |  | Likelihood:
[6 empty] | Consequence: |  | Consequence:
[6 empty] | Level of Risk: |  | Level of Risk:

## Enquiries, Issues and Meetings
Enquiries, Issues and Meetings
Enquiries or issues
Use the table below to record any enquiries or issues that have been raised relating to the contract. Ensure enough detail is included to support a new contract manager or assist in the redevelopment of the contract. Add rows as needed.
Date Received | Enquiry - Issue Details |  | Outcome - Resolution | Date Resolved | Significant | Contact Person | File/RMS Reference No.
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Yes / No
Meetings
Use the table below to record the details of any key meetings had related to the contract. This could include meetings with the contractor, customers, reference groups or any key stakeholders. Add rows as needed.
Stakeholder Name | Meeting Type | Meeting Date | Items raised | Actions | File/RMS Reference No.

## Reporting
Reporting
Use the table below to record the details of any reporting requirements of the contract. If applicable, include any WAIPS reporting requirements. Add rows as needed.
Report Type | Date Due | Date Received | Comments | Issues / Actions Requiring Follow Up | File/RMS Reference No.

## Stakeholder List
Stakeholder List
Use the table below to record any key stakeholders interested in the contract. This may include customers, reference group members or Executive members with delegated authority. Add rows as needed.
Name | Position | Organisation | Phone No. | Email | Comments

## Transition
Transition
Transition In
Use the tables below to record any tasks that need be completed during the transition in/out phases of the contract. Add rows as needed.
Transition In Task | Who | When | Comments
Transition Out
Transition Out Task | Who | When | Comments